## Checklist
Project Timeline Checklist
The Project Timeline is the official documentation of the budget and time frame of the project. The Project Timeline must be consistent with the Scope of Work and the Grant Application Cover Sheet. Applications with missing components will be at a competitive disadvantage.
The Project Timeline must:
| □ | Use the Fiscal Year 2020-21 template provided (do not alter the template) and submit in Microsoft Excel format.
| □ | List all tasks and sub-tasks with the same title as stated in the Scope of Work.
| □ | Include task and sub-task numbers in proper sequencing, consistent with the Scope of Work.
| □ | Include a task for a kick-off meeting with Caltrans at the start of the grant.
| □ | Include a task for procurement of consultants, if consultants are needed.
| □ | Include a task for quarterly reporting to Caltrans.
| □ | Include a task for invoicing.
| □ | List the responsible party for each task and sub-task, and ensure that it is consistent with the Scope of Work (i.e. applicant, sub-applicant, or consultant).
| □ | Complete all budget columns as appropriate: Total Cost, Grant Amount, Local Cash Match, and if applicable, Local In-Kind Match.
| □ | State a realistic total cost for each task based on the work that will be completed.
| □ | Project management/administration costs (e.g., quarterly reports, invoicing, project management meetings) should not exceed five percent of the grant amount requested
| □ | Include a proportional spread of local match amongst each task. The match amount must be at least the minimum amount required by the grant program.
| □ | Identify the indirect cost rate if indirect costs will be reimbursed.
| □ | Include a best estimate of the amount of time needed to complete each task.
| □ | Start the timeframe at the beginning of the grant period (July 2020 for MPO/RTPAs; September 2020 for non-MPO/RTPAs).
| □ | Extend the timeframe all the way to the end of the grant period (Project end dates differ based on applicant type and type of funds, i.e., State or federal. See Grant Application Guide, Pages 26-27, for details).
| □ | List the deliverable for each task as stated in the scope of work.

## Template
California Department of Transportation Transportation Planning Grants Fiscal Year 2020-21 Project Timeline
| Grantee: | [15 empty] | Project Title:
|  | Fund Source |  |  |  |  | Fiscal Year 2020/21 | [11 empty] | FY 2021/22 | [11 empty] | FY 2022/23
Task Number |  | Responsible Party | Total Cost | Grant Amount | Local Cash Match | Local In-Kind Match | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | Deliverables
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| TOTALS |  | 0 | 0 | 0 | 0
Reimbursement of indirect costs is allowable upon approval of an Indirect Cost Allocation Plan for each year of project activities. Provide rate if indirect costs are included in the project budget. Approved Indirect Cost Rate: ______%
Note: Each task must contain a grant amount and a local cash match amount. Local cash match must be proportionally distributed by the same percentage throughout each task. Local in-kind match needs to be indicated where in-kind services will be used. Please review the grant program section that you are applying to for details on local match requirements. The project timeline must be consistent with the scope of work.