## Examples
Inactive Project Current Cost Estimate Examples
Example 1:
Authorization Phase | Total Cost Amount |  | Federal Obligated Amount |  |  | Federal Amount Expended |  | Federal Unexpended Balance |  | Remaining Eligible Costs to be Incurred |  | Federal Obligations Needed
PE | 400000 |  | 350000 |  |  | 350000 |  | 0 |  | 0 |  | 0
ROW | 200000 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
CON | 5000000 |  | 4400000 |  |  | 4190000 |  | 210000 |  | 135000 |  | 135000
OTHER | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Total of All Phases | 5600000 |  | 4750000 |  |  | 4540000 |  | 210000 |  | 135000 |  | 135000
Estimated date to request next Federal reimbursement: 01/09/2022 (MM/DD/YYYY) Estimated date to fully expend Federal Obligation: 05/23/2022 (MM/DD/YYYY) Federal Amount to be deobligated: $75,000.00 Please provide a detailed description of the remaining eligible costs to be incurred: The Contractor has completed all work except for landscaping. The project still needs an estimated $95,000 for trees, irrigation and related landscaping items to be installed by the Contractor. 50 trees x $700 per tree: $35,000 PVC pipe, timing controllers, etc.: $60,000 Additionally, $40,000 is needed for remaining construction engineering costs:  City’s Resident Engineer: $100 per hour x 250 hours = $25,000  Inspector: $60 per hour x 250 hours = $15,000
Example 2 consultant contract:
Task |  | Total Cost |  | Percent Complete | Federal Amount Expended |  | Federal Unexpended Balance |  | Remaining Eligible Costs to be Incurred |  | Federal Obligations Needed
Project Admin Documents |  | 45000 |  | 50% | 22500 |  | 22500 |  | 22500 |  | 22500
Public Outreach |  | 23000 |  | 0% | 0 |  | 23000 |  | 23000 |  | 23000
90% PSE |  | 430000 |  | 100% | 365500 |  | 64500 |  | 0 |  | 0
Project Management |  | 200000 |  | 60% | 120000 |  | 80000 |  | 80000 |  | 80000
Total of All Costs |  | 698000 |  |  | 508000 |  | 190000 |  | 125500 |  | 125500
Due to cost savings in design, the full amount for 90% PSE is not needed. Estimated date to request next Federal reimbursement: 01/09/2022 (MM/DD/YYYY) Estimated date to fully expend Federal Obligation: 05/23/2022 (MM/DD/YYYY) Federal Amount to be deobligated: $64,500.00* *A de-obligation request shall be sent to the district for any unneeded unexpended federal funds remaining on the project.